## US
Task # | Week 1 | Duration | Start | Target | Completed | Resp Party | COV Notes | AFTON Notes
1 | Contract signed and complete |  |  |  |  | COV/AFT
2 | Initial meeting between Covington/Afton to review milestones |  |  |  |  | COV/AFT
3 | Obtain contacts, addresses etc. of Afton's global locations |  |  |  |  | COV
4 | Identify global Afton contacts (HR, IT, Security, etc.) |  |  |  |  | COV/AFT
5 | Identify client firewall and data security requirements if varied by region |  |  |  |  | COV/AFT
6 | Schedule weekly conference calls with Afton |  |  |  |  | COV/AFT
7 | Schedule weekly conference calls with BCD representatives |  |  |  |  | COV
8 | Establish internal implementation team |  |  |  |  | COV
9 | Authorization for negotiated airline contracts - DRA/ATPCO process |  |  |  |  | AFT
10 | Apply for ARC license/certifications if necessary |  |  |  |  | COV
11 | Review and revise global Afton policy requirements |  |  |  |  | COV/AFT
12 | Discuss profile loading process (HR feed, manual entry, etc.) |  |  |  |  | COV/AFT
13 | Hold internal and client kick-off meetings - set ground rules, conference call etiquette, reiterate email communication, etc. |  |  |  |  | COV
14 | Discuss escalation process - responsibility |  |  |  |  | COV
15 | Discuss implementation expenses (budget, pricing considerations, responsibility for approvals) |  |  |  |  | COV
16 | Obtain customer holiday schedule for global project team |  |  |  |  | COV/AFT
17 | Determine usage of POS transaction fee: if set at global level or permitted to be established locally |  |  |  |  | COV/AFT
18 | Will fees be per transaction, per pnr, life of PNR, charging for splits, car/hotel only |  |  |  |  | COV
19 | Afton Travel Policy distributed to International Rate Desk, Operations |  |  |  |  | COV
20 | Unique pseudo ordered and received from GDS as needed |  |  |  |  | COV
21 | Request department list - hierarchy |  |  |  |  | COV/AFT
22 | Set up customer ID - account established |  |  |  |  | COV
23 | Review reporting/accounting requirements - static and manual entry |  |  |  |  | COV/AFT
24 | Afton request for savings/reasons codes for review |  |  |  |  | COV/AFT
25 | Verify preferred vendors air, hotel and car rental discounts |  |  |  |  | COV/AFT
26 | Confirm KPI's, SLA's as required |  |  |  |  | COVAFT
27 | Establish Afton Travel Portal - present for Afton review |  |  |  |  | COV
30 | Request toll-free phone line(s) for 24/7 general and VIP |  |  |  |  | COV
31 | Delivered preferred hotel rate listing to for HIC table loading |  |  |  |  | COV
32 | Afton Travel Policy updated and attached to file |  |  |  |  | COV/AFT
33 | Review auto ticketing QC checks with online team and agent team |  |  |  |  | COV
34 | Submit the On-Line Booking Product order form |  |  |  |  | COV
35 | Define training and launch strategy for orientation |  |  |  |  | COV/AFT
36 | Review rollout communication methodology |  |  |  |  | COV/AFT
Weeks 2-3
37 | Direct process for installation of mobile apps and mobile notifications |  |  |  |  | COV
38 | Confirm accounting fields - static and non for use by online and traditional agents |  |  |  |  | COV/AFT
39 | Review past air, hotel and car rental volumes and determine plan to maximize savings |  |  |  |  | COV/AFT
40 | Discuss payment process - credit card designation |  |  |  |  | COV/AFT
41 | Global Account Manager and Client Services to meet with Afton to discuss timeline/duties |  |  |  |  | COVAFT
42 | Define traveler profile setup approach - HR feed or transfer |  |  |  |  | COV
43 | Discuss PNR finishing requirements |  |  |  |  | COV
44 | Setup traveler profiles |  |  |  |  | COV
45 | Load discount data |  |  |  |  | COV
46 | Complete branding |  |  |  |  | COV
47 | Develop online help content |  |  |  |  | COV
Week 4
48 | Schedule implementation/orientation sessions with travelers and travel coordinators |  |  |  |  | COV/ AFT
49 | Review any pre trip authorization processes and hierarchy |  |  |  |  | COV/AFT
50 | Clarify policy violation codes |  |  |  |  | COV/AFT
51 | Clarify fare refusal and fare savings rules |  |  |  |  | COV/AFT
52 | Review reporting requirements |  |  |  |  | COV/ AFT
53 | Create travel procedures instructions to publish on travel portal |  |  |  |  | COV
54 | Establish queue process with risk management/traveler tracking provider |  |  |  |  | COV
55 | Review instructions for online user information training |  |  |  |  | COV
56 | Determine online survey processes and frequency |  |  |  |  | COV
57 | Review Afton Travel portal and check links |  |  |  |  | COV
58 | Complete first agent training seminar |  |  |  |  | COV
59 | Revise training curriculum as needed and schedule follow up training |  |  |  |  | COV
60 | Complete sign-off - of online tool |  |  |  |  | COV
61 | Approve report formats |  |  |  |  | AFT
62 | Test run new reports |  |  |  |  | COV
63 | Test run QC checks |  |  |  |  | COV
64 | Set up webex and onsite training schedule for users |  |  |  |  | COV
65 | Online help desk review of procedures and Afton policies |  |  |  |  | COV
66 | Review client vendor relationships and pricing in GDS |  |  |  |  | COV
67 | Review check list of client profile with afterhours COV office |  |  |  |  | COV
68 | Review check list of procedures with online fulfillment desk/technical help desk |  |  |  |  | COV
69 | Schedule ongoing management contacts and weekly/monthly/quarterly account updates and reviews |  |  |  |  | COV/AFT
70 | Finalize global SLA/KPI parameters |  |  |  |  | COV/AFT
71 | Verity Travel Authorization routine working properly |  |  |  |  | COV/AFT
72 | Verify Afton client portal is complete |  |  |  |  | COV
73 | Perform online user training onsite and via web conferencing |  |  |  |  | COV/ AFT
74 | Review administrator access and knowledge of duties |  |  |  |  | COV/AFT
75 | Final training of Afton policies and procedures with designated travel consultants |  |  |  |  | COV
76 | Test all vendor pricing within online tool and through traditional methods |  |  |  |  | COV
77 | Verify accounting information for data collection |  |  |  |  | COV
78 | Check QC processes for policy and vendor compliance for pricing/Afton requirements |  |  |  |  | COV
79 | Official Start up new Afton contract

## Canada
Task # | Weeks 1-3 | Duration | Start | Target | Completed | Resp Party | COVBCD Notes | AFTON Notes
1 | Contract signed and complete |  |  |  |  | COVBCD/ AFT
2 | Initial meeting between Covington/Afton to review milestones |  |  |  |  | COV/AFT
3 | Introduction of local BCD staff and regional Afton travel administrators |  |  |  |  | COVCBCD/ AFT
4 | Obtain contacts, addresses etc. of Afton's global locations |  |  |  |  | COV
5 | Identify global Afton contacts (HR, IT, Security, etc.) |  |  |  |  | COV/AFT
6 | Identify client firewall and data security requirements if varied by region |  |  |  |  | COV/AFT
7 | Set up call with project initiator to review the completed Global Project Initiation Document (PID) |  |  |  |  | COVBCD/ AFT
8 | Schedule weekly conference calls with Afton |  |  |  |  | COV/AFT
9 | Schedule weekly conference calls with BCD representatives |  |  |  |  | COVBCD
10 | Establish internal implementation team |  |  |  |  | COV
11 | Authorization for negotiated airline contracts - DRA/ATPCO process |  |  |  |  | AFT
12 | Advise client to alert all vendors with contracts of agency change |  |  |  |  | COV/AFT
13 | Determine deployment strategy of regional service - finalize check list |  |  |  |  | COVBCD/ AFT
14 | Apply for ARC license/certifications |  |  |  |  | COVBCD
15 | Review and revise global Afton policy requirements |  |  |  |  | COVBCD/ AFT
16 | Review and revise regional policy parameters |  |  |  |  | COVBCD/ AFT
17 | Discuss profile loading process (HR feed, manual entry, etc.) |  |  |  |  | COVBCD/ AFT
18 | Hold internal and client kick-off meetings - set ground rules, conference call etiquette, reiterate email communication, etc. |  |  |  |  | COV
19 | Discuss escalation process - responsibility |  |  |  |  | COV
20 | Discuss implementation expenses (budget, pricing considerations, responsibility for approvals) |  |  |  |  | COV
21 | Obtain customer holiday schedule for global project team |  |  |  |  | COV/AFT
22 | Determine usage of POS transaction fee: if set at global level or permitted to be established locally |  |  |  |  | COVBCD/ AFT
23 | Will fees be per transaction, per pnr, life of PNR, charging for splits, car/hotel only |  |  |  |  | COVBCD
24 | Afton Travel Policy distributed to International Rate Desk, Operations, |  |  |  |  | COVBCD
25 | Unique pseudo ordered and received from GDS as needed |  |  |  |  | COVBCD
26 | Request department list - hierarchy |  |  |  |  | COVBCD/ AFT
27 | Set up customer ID - account established |  |  |  |  | COVBCD
28 | Review reporting/accounting requirements - static and manual entry |  |  |  |  | COVBCD/ AFT
29 | Afton request for savings/reasons codes for review |  |  |  |  | COVBCD/ AFT
30 | Verify preferred vendors air, hotel and car rental discounts |  |  |  |  | COVBCD/ AFT
31 | Confirm KPI's, SLA's as required |  |  |  |  | COVBCD/ AFT
32 | Establish Afton Travel Portal - present for Afton review |  |  |  |  | COV
33 | Preferred vendor contacts delivered to COVBCD |  |  |  |  | COVBCD/ AFT
34 | Discuss project milestones |  |  |  |  | COVBCD/ AFT
35 | Request toll-free phone line(s) for 24/7 general and VIP |  |  |  |  | COVBCD
36 | Delivered preferred hotel rate listing to for HIC table loading |  |  |  |  | COVBCD
37 | Afton Travel Policy updated and attached to file |  |  |  |  | COV/AFT
38 | Review auto ticketing QC checks with online team and agent team |  |  |  |  | COVBCD
39 | Profile entry review, COVBCD processes |  |  |  |  | COVBCD/ AFT
40 | BCD meeting with Afton, determine official start date |  |  |  |  | COVBCD/ AFT
41 | Advise client to alert credit card vendor of agency change |  |  |  |  | COVBCD
42 | Determine local region airline contracts - receive copies |  |  |  |  | COVBCD/ AFT
43 | Determine Small Biz programs: need corporate id numbers |  |  |  |  | COVBCD/ AFT
44 | Add ARC/pseudos to airline hard and small biz agreements |  |  |  |  | COVBCD/ AFT
45 | Request client name list/e-mail addresses -VIP |  |  |  |  | COVBCD/ AFT
46 | Submit the On-Line Booking Product order form |  |  |  |  | COVBCD
47 | Define training and launch strategy for orientation |  |  |  |  | COVBCD/ AFT
48 | Review rollout communication methodology |  |  |  |  | COV/AFT
Task # | Weeks 4-6
49 | Review travel policies, identify regional differences and update |  |  |  |  | COVBCD/ AFT
50 | Confirm GDS client Star for accuracy |  |  |  |  | COVBCD/ AFT
51 | Direct process for installation of mobile apps and mobile notifications |  |  |  |  | COVBCD
52 | Establish dedicated Afton email address as needed |  |  |  |  | COV/AFT
53 | Confirm accounting fields - static and non for use by online and traditional agents |  |  |  |  | COVBCD/ AFT
54 | Review past air, hotel and car rental volumes and determine plan to maximize savings |  |  |  |  | COVBCD/ AFT
55 | Update project plan with milestones |  |  |  |  | COVBCD
56 | Notify 24-hour Emergency Service Centers of new client |  |  |  |  | COVBCD
57 | Discuss payment process - credit card designation |  |  |  |  | COV/AFT
58 | Increased staff confirmed for Fairfax support - August 1 start |  |  |  |  | COVBCD
59 | Global Account Manager and Client Services to meet with Afton to discuss timeline/duties |  |  |  |  | COVBCD/ AFT
60 | Confirm Afton phone config combined with COVBCD |  |  |  |  | COVBCD/ AFT
61 | Define traveler profile setup approach - HR feed or transfer |  |  |  |  | COVBCD
62 | Discuss PNR finishing requirements |  |  |  |  | COVBCD
63 | Setup traveler profiles |  |  |  |  | COVBCD
64 | Load discount data |  |  |  |  | COVBCD
65 | Load agency fees to profile |  |  |  |  | COVBCD
66 | Complete branding |  |  |  |  | COV
67 | Develop online help content |  |  |  |  | COV
Task # | Weeks 7-8
68 | Confirm ATPCO loading with airlines for release of data from COVBCD |  |  |  |  | COV
69 | Confirm designated agent grouping |  |  |  |  | COVBCD
70 | Schedule implementation/orientation session with travelers and travel coordinators |  |  |  |  | COVBCD/ AFT
71 | Confirm required accounting fields |  |  |  |  | COV/AFT
72 | Program online tool with policies and preferred vendors where applicable |  |  |  |  | COVBCD
73 | Program quality control systems with Afton policies and preferred vendors and test accuracy |  |  |  |  | COVBCD
74 | Test profile synchronization to GDS/online tool |  |  |  |  | COVBCD
75 | Review any pre trip authorization processes and hierarchy |  |  |  |  | COV/AFT
76 | Clarify policy violation codes |  |  |  |  | COV/AFT
77 | Clarify fare refusal and fare savings rules |  |  |  |  | COV/AFT
78 | Review reporting requirements |  |  |  |  | COVBCD/ AFT
79 | Create travel procedures instructions to publish on travel portal |  |  |  |  | COV
80 | Review required reporting |  |  |  |  | COVBCD/ AFT
81 | Discuss and clarify fare refusal and fare savings with client/agents and test online consistency |  |  |  |  | COVBCD
82 | Review Quality Control checks |  |  |  |  | COVBCD
83 | Online functional overview (WebEx meeting) |  |  |  |  | COV
84 | Deliver Online logins to project team |  |  |  |  | COV
85 | Select WebDirect sites to search |  |  |  |  | COVBCD
86 | Exclude vendors |  |  |  |  | COVBCD
87 | Plan training program |  |  |  |  | COV/AFT
88 | Review training curriculum |  |  |  |  | COV/AFT
89 | Print training materials |  |  |  |  | COV/AFT
90 | Schedule administrator training |  |  |  |  | COVBCD/ AFT
91 | Schedule travel coordinator training |  |  |  |  | COVBCD/ AFT
92 | Schedule user training |  |  |  |  | COVBCD/ AFT
Task # | Weeks 9 and 10
93 | Conference call with Afton to review progress |  |  |  |  | COV/AFT
94 | Meet with client locally to review timeline |  |  |  |  | BCD/AFT
95 | Discuss accounting data and verify reporting requirements |  |  |  |  | COVBCD/ AFT
96 | Test preferred vendor and discount accuracy |  |  |  |  | COVBCD
97 | Establish queue process with risk management/traveler tracking provider |  |  |  |  | COVBCD
98 | Review instructions for online user information training |  |  |  |  | COV
99 | Determine online survey processes and frequency |  |  |  |  | COV
100 | Review Afton Travel portal and check links |  |  |  |  | COVBCD
101 | Complete first agent training seminar |  |  |  |  | COVBCD
102 | Revise training curriculum as needed and schedule follow up training |  |  |  |  | COVBCD
103 | Validate PNR is finished correctly and in proper queue(s) |  |  |  |  | COVBCD
104 | Verify travel policy and approval/notification |  |  |  |  | COVBCD/ AFT
105 | Complete sign-off - of online tool |  |  |  |  | COVBCD
106 | Send introduction letter to travelers |  |  |  |  | COV/AFT
107 | Inform agents and support staff "go live" date |  |  |  |  | COVBCD
108 | Review with fulfillment center and 24-hour emergency service centers |  |  |  |  | COVBCD
109 | Establish Afton customized reports or dashboards |  |  |  |  | COVBCD
110 | Establish Afton Travel Portal and test |  |  |  |  | COVBCD
111 | Complete second agent training seminar |  |  |  |  | COV
112 | Review new report formats |  |  |  |  | COV/AFT
113 | Approve report formats |  |  |  |  | AFT
114 | Test run new reports |  |  |  |  | COVBCD
115 | Review profile set up, client passwords, procedures defined |  |  |  |  | COVBCD
116 | Establish email notification for online users as to traveler profile set up |  |  |  |  | COVBCD
117 | Establish timeline and deadlines for profile loading |  |  |  |  | COVBCD
118 | Test profile format and verify accounting information is loading correctly in GDS |  |  |  |  | COVBCD
119 | Test run QC checks |  |  |  |  | COVBCD
120 | Set up webex and onsite training schedule for users |  |  |  |  | COVBCD
121 | Online help desk review of procedures and Afton policies |  |  |  |  | COV
Task # | Week 11 and 12
122 | Review client vendor relationships and pricing in GDS |  |  |  |  | COVBCD
123 | Review check list of client profile with afterhours COVBCD office |  |  |  |  | COVBCD
124 | Review check list of procedures with online fulfillment desk/technical help desk |  |  |  |  | COVBCD
125 | Schedule ongoing management contacts and weekly/monthly/quarterly account updates and reviews |  |  |  |  | COV/AFT
126 | Finalize global SLA/KPI parameters |  |  |  |  | COV/AFT
127 | Verity Travel Authorization routine working properly |  |  |  |  | COV/AFT
128 | Verify Afton client portal is complete |  |  |  |  | COV
129 | Perform online user training onsite and via web conferencing |  |  |  |  | COVBCD/ AFT
130 | Review administrator access and knowledge of duties |  |  |  |  | COV/AFT
131 | Final training of Afton policies and procedures with designated travel consultants |  |  |  |  | COVBCD
132 | Test all vendor pricing within online tool and through traditional methods |  |  |  |  | COVBCD
133 | Verify accounting information for data collection |  |  |  |  | COVBCD
134 | Check QC processes for policy and vendor compliance for pricing/Afton requirements |  |  |  |  | COVBCD
135 | Profile loading initiated by travelers and users |  |  |  |  | COV/AFT
136 | Test profile data for accuracy in data loading |  |  |  |  | COVBCD
Official Start up of Afton

## EMEA
Task # | Weeks 1-3 | Duration | Start | Target | Completed | Resp Party | COVBCD Notes | AFTON Notes
1 | Contract signed and complete |  |  |  |  | COVBCD/ AFT
2 | Initial meeting between Covington/Afton to review milestones |  |  |  |  | COV/AFT
3 | Introduction of local BCD staff and regional Afton travel administrators |  |  |  |  | COVCBCD/ AFT
4 | Obtain contacts, addresses etc. of Afton's global locations |  |  |  |  | COV
5 | Identify global Afton contacts (HR, IT, Security, etc.) |  |  |  |  | COV/AFT
6 | Identify client firewall and data security requirements if varied by region |  |  |  |  | COV/AFT
7 | Set up call with project initiator to review the completed Global Project Initiation Document (PID) |  |  |  |  | COVBCD/ AFT
8 | Schedule weekly conference calls with Afton |  |  |  |  | COV/AFT
9 | Schedule weekly conference calls with BCD representatives |  |  |  |  | COVBCD
10 | Establish internal implementation team |  |  |  |  | COV
11 | Authorization for negotiated airline contracts - DRA/ATPCO process |  |  |  |  | AFT
12 | Advise client to alert all vendors with contracts of agency change |  |  |  |  | COV/AFT
13 | Determine deployment strategy of regional service - finalize check list |  |  |  |  | COVBCD/ AFT
14 | Apply for ARC license/certifications |  |  |  |  | COVBCD
15 | Review and revise global Afton policy requirements |  |  |  |  | COVBCD/ AFT
16 | Review and revise regional policy parameters |  |  |  |  | COVBCD/ AFT
17 | Discuss profile loading process (HR feed, manual entry, etc.) |  |  |  |  | COVBCD/ AFT
18 | Hold internal and client kick-off meetings - set ground rules, conference call etiquette, reiterate email communication, etc. |  |  |  |  | COV
19 | Discuss escalation process - responsibility |  |  |  |  | COV
20 | Discuss implementation expenses (budget, pricing considerations, responsibility for approvals) |  |  |  |  | COV
21 | Obtain customer holiday schedule for global project team |  |  |  |  | COV/AFT
22 | Determine usage of POS transaction fee: if set at global level or permitted to be established locally |  |  |  |  | COVBCD/ AFT
23 | Will fees be per transaction, per pnr, life of PNR, charging for splits, car/hotel only |  |  |  |  | COVBCD
24 | Afton Travel Policy distributed to International Rate Desk, Operations, |  |  |  |  | COVBCD
25 | Unique pseudo ordered and received from GDS as needed |  |  |  |  | COVBCD
26 | Request department list - hierarchy |  |  |  |  | COVBCD/ AFT
27 | Set up customer ID - account established |  |  |  |  | COVBCD
28 | Review reporting/accounting requirements - static and manual entry |  |  |  |  | COVBCD/ AFT
29 | Afton request for savings/reasons codes for review |  |  |  |  | COVBCD/ AFT
30 | Verify preferred vendors air, hotel and car rental discounts |  |  |  |  | COVBCD/ AFT
31 | Confirm KPI's, SLA's as required |  |  |  |  | COVBCD/ AFT
32 | Establish Afton Travel Portal - present for Afton review |  |  |  |  | COV
33 | Preferred vendor contacts delivered to COVBCD |  |  |  |  | COVBCD/ AFT
34 | Discuss project milestones |  |  |  |  | COVBCD/ AFT
35 | Request toll-free phone line(s) for 24/7 general and VIP |  |  |  |  | COVBCD
36 | Delivered preferred hotel rate listing to for HIC table loading |  |  |  |  | COVBCD
37 | Afton Travel Policy updated and attached to file |  |  |  |  | COV/AFT
38 | Review auto ticketing QC checks with online team and agent team |  |  |  |  | COVBCD
39 | Profile entry review, COVBCD processes |  |  |  |  | COVBCD/ AFT
40 | BCD meeting with Afton, determine official start date |  |  |  |  | COVBCD/ AFT
41 | Advise client to alert credit card vendor of agency change |  |  |  |  | COVBCD
42 | Determine local region airline contracts - receive copies |  |  |  |  | COVBCD/ AFT
43 | Determine Small Biz programs: need corporate id numbers |  |  |  |  | COVBCD/ AFT
44 | Add ARC/pseudos to airline hard and small biz agreements |  |  |  |  | COVBCD/ AFT
45 | Request client name list/e-mail addresses -VIP |  |  |  |  | COVBCD/ AFT
46 | Submit the On-Line Booking Product order form |  |  |  |  | COVBCD
47 | Define training and launch strategy for orientation |  |  |  |  | COVBCD/ AFT
48 | Review rollout communication methodology |  |  |  |  | COV/AFT
Task # | Weeks 4-6
49 | Review travel policies, identify regional differences and update |  |  |  |  | COVBCD/ AFT
50 | Confirm GDS client Star for accuracy |  |  |  |  | COVBCD/ AFT
51 | Direct process for installation of mobile apps and mobile notifications |  |  |  |  | COVBCD
52 | Establish dedicated Afton email address as needed |  |  |  |  | COV/AFT
53 | Confirm accounting fields - static and non for use by online and traditional agents |  |  |  |  | COVBCD/ AFT
54 | Review past air, hotel and car rental volumes and determine plan to maximize savings |  |  |  |  | COVBCD/ AFT
55 | Update project plan with milestones |  |  |  |  | COVBCD
56 | Notify 24-hour Emergency Service Centers of new client |  |  |  |  | COVBCD
57 | Discuss payment process - credit card designation |  |  |  |  | COV/AFT
58 | Increased staff confirmed for Fairfax support - August 1 start |  |  |  |  | COVBCD
59 | Global Account Manager and Client Services to meet with Afton to discuss timeline/duties |  |  |  |  | COVBCD/ AFT
60 | Confirm Afton phone config combined with COVBCD |  |  |  |  | COVBCD/ AFT
61 | Define traveler profile setup approach - HR feed or transfer |  |  |  |  | COVBCD
62 | Discuss PNR finishing requirements |  |  |  |  | COVBCD
63 | Setup traveler profiles |  |  |  |  | COVBCD
64 | Load discount data |  |  |  |  | COVBCD
65 | Load agency fees to profile |  |  |  |  | COVBCD
66 | Complete branding |  |  |  |  | COV
67 | Develop online help content |  |  |  |  | COV
Task # | Weeks 7-8
68 | Confirm ATPCO loading with airlines for release of data from COVBCD |  |  |  |  | COV
69 | Confirm designated agent grouping |  |  |  |  | COVBCD
70 | Schedule implementation/orientation session with travelers and travel coordinators |  |  |  |  | COVBCD/ AFT
71 | Confirm required accounting fields |  |  |  |  | COV/AFT
72 | Program online tool with policies and preferred vendors where applicable |  |  |  |  | COVBCD
73 | Program quality control systems with Afton policies and preferred vendors and test accuracy |  |  |  |  | COVBCD
74 | Test profile synchronization to GDS/online tool |  |  |  |  | COVBCD
75 | Review any pre trip authorization processes and hierarchy |  |  |  |  | COV/AFT
76 | Clarify policy violation codes |  |  |  |  | COV/AFT
77 | Clarify fare refusal and fare savings rules |  |  |  |  | COV/AFT
78 | Review reporting requirements |  |  |  |  | COVBCD/ AFT
79 | Create travel procedures instructions to publish on travel portal |  |  |  |  | COV
80 | Review required reporting |  |  |  |  | COVBCD/ AFT
81 | Discuss and clarify fare refusal and fare savings with client/agents and test online consistency |  |  |  |  | COVBCD
82 | Review Quality Control checks |  |  |  |  | COVBCD
83 | Online functional overview (WebEx meeting) |  |  |  |  | COV
84 | Deliver Online logins to project team |  |  |  |  | COV
85 | Select WebDirect sites to search |  |  |  |  | COVBCD
86 | Exclude vendors |  |  |  |  | COVBCD
87 | Plan training program |  |  |  |  | COV/AFT
88 | Review training curriculum |  |  |  |  | COV/AFT
89 | Print training materials |  |  |  |  | COV/AFT
90 | Schedule administrator training |  |  |  |  | COVBCD/ AFT
91 | Schedule travel coordinator training |  |  |  |  | COVBCD/ AFT
92 | Schedule user training |  |  |  |  | COVBCD/ AFT
Task # | Weeks 9 and 10
93 | Conference call with Afton to review progress |  |  |  |  | COV/AFT
94 | Meet with client locally to review timeline |  |  |  |  | BCD/AFT
95 | Discuss accounting data and verify reporting requirements |  |  |  |  | COVBCD/ AFT
96 | Test preferred vendor and discount accuracy |  |  |  |  | COVBCD
97 | Establish queue process with risk management/traveler tracking provider |  |  |  |  | COVBCD
98 | Review instructions for online user information training |  |  |  |  | COV
99 | Determine online survey processes and frequency |  |  |  |  | COV
100 | Review Afton Travel portal and check links |  |  |  |  | COVBCD
101 | Complete first agent training seminar |  |  |  |  | COVBCD
102 | Revise training curriculum as needed and schedule follow up training |  |  |  |  | COVBCD
103 | Validate PNR is finished correctly and in proper queue(s) |  |  |  |  | COVBCD
104 | Verify travel policy and approval/notification |  |  |  |  | COVBCD/ AFT
105 | Complete sign-off - of online tool |  |  |  |  | COVBCD
106 | Send introduction letter to travelers |  |  |  |  | COV/AFT
107 | Inform agents and support staff "go live" date |  |  |  |  | COVBCD
108 | Review with fulfillment center and 24-hour emergency service centers |  |  |  |  | COVBCD
109 | Establish Afton customized reports or dashboards |  |  |  |  | COVBCD
110 | Establish Afton Travel Portal and test |  |  |  |  | COVBCD
111 | Complete second agent training seminar |  |  |  |  | COV
112 | Review new report formats |  |  |  |  | COV/AFT
113 | Approve report formats |  |  |  |  | AFT
114 | Test run new reports |  |  |  |  | COVBCD
115 | Review profile set up, client passwords, procedures defined |  |  |  |  | COVBCD
116 | Establish email notification for online users as to traveler profile set up |  |  |  |  | COVBCD
117 | Establish timeline and deadlines for profile loading |  |  |  |  | COVBCD
118 | Test profile format and verify accounting information is loading correctly in GDS |  |  |  |  | COVBCD
119 | Test run QC checks |  |  |  |  | COVBCD
120 | Set up webex and onsite training schedule for users |  |  |  |  | COVBCD
121 | Online help desk review of procedures and Afton policies |  |  |  |  | COV
Task # | Week 11 and 12
122 | Review client vendor relationships and pricing in GDS |  |  |  |  | COVBCD
123 | Review check list of client profile with afterhours COVBCD office |  |  |  |  | COVBCD
124 | Review check list of procedures with online fulfillment desk/technical help desk |  |  |  |  | COVBCD
125 | Schedule ongoing management contacts and weekly/monthly/quarterly account updates and reviews |  |  |  |  | COV/AFT
126 | Finalize global SLA/KPI parameters |  |  |  |  | COV/AFT
127 | Verity Travel Authorization routine working properly |  |  |  |  | COV/AFT
128 | Verify Afton client portal is complete |  |  |  |  | COV
129 | Perform online user training onsite and via web conferencing |  |  |  |  | COVBCD/ AFT
130 | Review administrator access and knowledge of duties |  |  |  |  | COV/AFT
131 | Final training of Afton policies and procedures with designated travel consultants |  |  |  |  | COVBCD
132 | Test all vendor pricing within online tool and through traditional methods |  |  |  |  | COVBCD
133 | Verify accounting information for data collection |  |  |  |  | COVBCD
134 | Check QC processes for policy and vendor compliance for pricing/Afton requirements |  |  |  |  | COVBCD
135 | Profile loading initiated by travelers and users |  |  |  |  | COV/AFT
136 | Test profile data for accuracy in data loading |  |  |  |  | COVBCD
Official Start up of Afton

## APAC
Task # | Weeks 1-3 | Duration | Start | Target | Completed | Resp Party | COVBCD Notes | AFTON Notes
1 | Contract signed and complete |  |  |  |  | COVBCD/ AFT
2 | Initial meeting between Covington/Afton to review milestones |  |  |  |  | COV/AFT
3 | Introduction of local BCD staff and regional Afton travel administrators |  |  |  |  | COVCBCD/ AFT
4 | Obtain contacts, addresses etc. of Afton's global locations |  |  |  |  | COV
5 | Identify global Afton contacts (HR, IT, Security, etc.) |  |  |  |  | COV/AFT
6 | Identify client firewall and data security requirements if varied by region |  |  |  |  | COV/AFT
7 | Set up call with project initiator to review the completed Global Project Initiation Document (PID) |  |  |  |  | COVBCD/ AFT
8 | Schedule weekly conference calls with Afton |  |  |  |  | COV/AFT
9 | Schedule weekly conference calls with BCD representatives |  |  |  |  | COVBCD
10 | Establish internal implementation team |  |  |  |  | COV
11 | Authorization for negotiated airline contracts - DRA/ATPCO process |  |  |  |  | AFT
12 | Advise client to alert all vendors with contracts of agency change |  |  |  |  | COV/AFT
13 | Determine deployment strategy of regional service - finalize check list |  |  |  |  | COVBCD/ AFT
14 | Apply for ARC license/certifications |  |  |  |  | COVBCD
15 | Review and revise global Afton policy requirements |  |  |  |  | COVBCD/ AFT
16 | Review and revise regional policy parameters |  |  |  |  | COVBCD/ AFT
17 | Discuss profile loading process (HR feed, manual entry, etc.) |  |  |  |  | COVBCD/ AFT
18 | Hold internal and client kick-off meetings - set ground rules, conference call etiquette, reiterate email communication, etc. |  |  |  |  | COV
19 | Discuss escalation process - responsibility |  |  |  |  | COV
20 | Discuss implementation expenses (budget, pricing considerations, responsibility for approvals) |  |  |  |  | COV
21 | Obtain customer holiday schedule for global project team |  |  |  |  | COV/AFT
22 | Determine usage of POS transaction fee: if set at global level or permitted to be established locally |  |  |  |  | COVBCD/ AFT
23 | Will fees be per transaction, per pnr, life of PNR, charging for splits, car/hotel only |  |  |  |  | COVBCD
24 | Afton Travel Policy distributed to International Rate Desk, Operations, |  |  |  |  | COVBCD
25 | Unique pseudo ordered and received from GDS as needed |  |  |  |  | COVBCD
26 | Request department list - hierarchy |  |  |  |  | COVBCD/ AFT
27 | Set up customer ID - account established |  |  |  |  | COVBCD
28 | Review reporting/accounting requirements - static and manual entry |  |  |  |  | COVBCD/ AFT
29 | Afton request for savings/reasons codes for review |  |  |  |  | COVBCD/ AFT
30 | Verify preferred vendors air, hotel and car rental discounts |  |  |  |  | COVBCD/ AFT
31 | Confirm KPI's, SLA's as required |  |  |  |  | COVBCD/ AFT
32 | Establish Afton Travel Portal - present for Afton review |  |  |  |  | COV
33 | Preferred vendor contacts delivered to COVBCD |  |  |  |  | COVBCD/ AFT
34 | Discuss project milestones |  |  |  |  | COVBCD/ AFT
35 | Request toll-free phone line(s) for 24/7 general and VIP |  |  |  |  | COVBCD
36 | Delivered preferred hotel rate listing to for HIC table loading |  |  |  |  | COVBCD
37 | Afton Travel Policy updated and attached to file |  |  |  |  | COV/AFT
38 | Review auto ticketing QC checks with online team and agent team |  |  |  |  | COVBCD
39 | Profile entry review, COVBCD processes |  |  |  |  | COVBCD/ AFT
40 | BCD meeting with Afton, determine official start date |  |  |  |  | COVBCD/ AFT
41 | Advise client to alert credit card vendor of agency change |  |  |  |  | COVBCD
42 | Determine local region airline contracts - receive copies |  |  |  |  | COVBCD/ AFT
43 | Determine Small Biz programs: need corporate id numbers |  |  |  |  | COVBCD/ AFT
44 | Add ARC/pseudos to airline hard and small biz agreements |  |  |  |  | COVBCD/ AFT
45 | Request client name list/e-mail addresses -VIP |  |  |  |  | COVBCD/ AFT
46 | Submit the On-Line Booking Product order form |  |  |  |  | COVBCD
47 | Define training and launch strategy for orientation |  |  |  |  | COVBCD/ AFT
48 | Review rollout communication methodology |  |  |  |  | COV/AFT
Task # | Weeks 4-6
49 | Review travel policies, identify regional differences and update |  |  |  |  | COVBCD/ AFT
50 | Confirm GDS client Star for accuracy |  |  |  |  | COVBCD/ AFT
51 | Direct process for installation of mobile apps and mobile notifications |  |  |  |  | COVBCD
52 | Establish dedicated Afton email address as needed |  |  |  |  | COV/AFT
53 | Confirm accounting fields - static and non for use by online and traditional agents |  |  |  |  | COVBCD/ AFT
54 | Review past air, hotel and car rental volumes and determine plan to maximize savings |  |  |  |  | COVBCD/ AFT
55 | Update project plan with milestones |  |  |  |  | COVBCD
56 | Notify 24-hour Emergency Service Centers of new client |  |  |  |  | COVBCD
57 | Discuss payment process - credit card designation |  |  |  |  | COV/AFT
58 | Increased staff confirmed for Fairfax support - August 1 start |  |  |  |  | COVBCD
59 | Global Account Manager and Client Services to meet with Afton to discuss timeline/duties |  |  |  |  | COVBCD/ AFT
60 | Confirm Afton phone config combined with COVBCD |  |  |  |  | COVBCD/ AFT
61 | Define traveler profile setup approach - HR feed or transfer |  |  |  |  | COVBCD
62 | Discuss PNR finishing requirements |  |  |  |  | COVBCD
63 | Setup traveler profiles |  |  |  |  | COVBCD
64 | Load discount data |  |  |  |  | COVBCD
65 | Load agency fees to profile |  |  |  |  | COVBCD
66 | Complete branding |  |  |  |  | COV
67 | Develop online help content |  |  |  |  | COV
Task # | Weeks 7-8
68 | Confirm ATPCO loading with airlines for release of data from COVBCD |  |  |  |  | COV
69 | Confirm designated agent grouping |  |  |  |  | COVBCD
70 | Schedule implementation/orientation session with travelers and travel coordinators |  |  |  |  | COVBCD/ AFT
71 | Confirm required accounting fields |  |  |  |  | COV/AFT
72 | Program online tool with policies and preferred vendors where applicable |  |  |  |  | COVBCD
73 | Program quality control systems with Afton policies and preferred vendors and test accuracy |  |  |  |  | COVBCD
74 | Test profile synchronization to GDS/online tool |  |  |  |  | COVBCD
75 | Review any pre trip authorization processes and hierarchy |  |  |  |  | COV/AFT
76 | Clarify policy violation codes |  |  |  |  | COV/AFT
77 | Clarify fare refusal and fare savings rules |  |  |  |  | COV/AFT
78 | Review reporting requirements |  |  |  |  | COVBCD/ AFT
79 | Create travel procedures instructions to publish on travel portal |  |  |  |  | COV
80 | Review required reporting |  |  |  |  | COVBCD/ AFT
81 | Discuss and clarify fare refusal and fare savings with client/agents and test online consistency |  |  |  |  | COVBCD
82 | Review Quality Control checks |  |  |  |  | COVBCD
83 | Online functional overview (WebEx meeting) |  |  |  |  | COV
84 | Deliver Online logins to project team |  |  |  |  | COV
85 | Select WebDirect sites to search |  |  |  |  | COVBCD
86 | Exclude vendors |  |  |  |  | COVBCD
87 | Plan training program |  |  |  |  | COV/AFT
88 | Review training curriculum |  |  |  |  | COV/AFT
89 | Print training materials |  |  |  |  | COV/AFT
90 | Schedule administrator training |  |  |  |  | COVBCD/ AFT
91 | Schedule travel coordinator training |  |  |  |  | COVBCD/ AFT
92 | Schedule user training |  |  |  |  | COVBCD/ AFT
Task # | Weeks 9 and 10
93 | Conference call with Afton to review progress |  |  |  |  | COV/AFT
94 | Meet with client locally to review timeline |  |  |  |  | BCD/AFT
95 | Discuss accounting data and verify reporting requirements |  |  |  |  | COVBCD/ AFT
96 | Test preferred vendor and discount accuracy |  |  |  |  | COVBCD
97 | Establish queue process with risk management/traveler tracking provider |  |  |  |  | COVBCD
98 | Review instructions for online user information training |  |  |  |  | COV
99 | Determine online survey processes and frequency |  |  |  |  | COV
100 | Review Afton Travel portal and check links |  |  |  |  | COVBCD
101 | Complete first agent training seminar |  |  |  |  | COVBCD
102 | Revise training curriculum as needed and schedule follow up training |  |  |  |  | COVBCD
103 | Validate PNR is finished correctly and in proper queue(s) |  |  |  |  | COVBCD
104 | Verify travel policy and approval/notification |  |  |  |  | COVBCD/ AFT
105 | Complete sign-off - of online tool |  |  |  |  | COVBCD
106 | Send introduction letter to travelers |  |  |  |  | COV/AFT
107 | Inform agents and support staff "go live" date |  |  |  |  | COVBCD
108 | Review with fulfillment center and 24-hour emergency service centers |  |  |  |  | COVBCD
109 | Establish Afton customized reports or dashboards |  |  |  |  | COVBCD
110 | Establish Afton Travel Portal and test |  |  |  |  | COVBCD
111 | Complete second agent training seminar |  |  |  |  | COV
112 | Review new report formats |  |  |  |  | COV/AFT
113 | Approve report formats |  |  |  |  | AFT
114 | Test run new reports |  |  |  |  | COVBCD
115 | Review profile set up, client passwords, procedures defined |  |  |  |  | COVBCD
116 | Establish email notification for online users as to traveler profile set up |  |  |  |  | COVBCD
117 | Establish timeline and deadlines for profile loading |  |  |  |  | COVBCD
118 | Test profile format and verify accounting information is loading correctly in GDS |  |  |  |  | COVBCD
119 | Test run QC checks |  |  |  |  | COVBCD
120 | Set up webex and onsite training schedule for users |  |  |  |  | COVBCD
121 | Online help desk review of procedures and Afton policies |  |  |  |  | COV
Task # | Week 11 and 12
122 | Review client vendor relationships and pricing in GDS |  |  |  |  | COVBCD
123 | Review check list of client profile with afterhours COVBCD office |  |  |  |  | COVBCD
124 | Review check list of procedures with online fulfillment desk/technical help desk |  |  |  |  | COVBCD
125 | Schedule ongoing management contacts and weekly/monthly/quarterly account updates and reviews |  |  |  |  | COV/AFT
126 | Finalize global SLA/KPI parameters |  |  |  |  | COV/AFT
127 | Verity Travel Authorization routine working properly |  |  |  |  | COV/AFT
128 | Verify Afton client portal is complete |  |  |  |  | COV
129 | Perform online user training onsite and via web conferencing |  |  |  |  | COVBCD/ AFT
130 | Review administrator access and knowledge of duties |  |  |  |  | COV/AFT
131 | Final training of Afton policies and procedures with designated travel consultants |  |  |  |  | COVBCD
132 | Test all vendor pricing within online tool and through traditional methods |  |  |  |  | COVBCD
133 | Verify accounting information for data collection |  |  |  |  | COVBCD
134 | Check QC processes for policy and vendor compliance for pricing/Afton requirements |  |  |  |  | COVBCD
135 | Profile loading initiated by travelers and users |  |  |  |  | COV/AFT
136 | Test profile data for accuracy in data loading |  |  |  |  | COVBCD
Official Start up of Afton

## Latin America
Task # | Weeks 1-3 | Duration | Start | Target | Completed | Resp Party | COVBCD Notes | AFTON Notes
1 | Contract signed and complete |  |  |  |  | COVBCD/ AFT
2 | Initial meeting between Covington/Afton to review milestones |  |  |  |  | COV/AFT
3 | Introduction of local BCD staff and regional Afton travel administrators |  |  |  |  | COVCBCD/ AFT
4 | Obtain contacts, addresses etc. of Afton's global locations |  |  |  |  | COV
5 | Identify global Afton contacts (HR, IT, Security, etc.) |  |  |  |  | COV/AFT
6 | Identify client firewall and data security requirements if varied by region |  |  |  |  | COV/AFT
7 | Set up call with project initiator to review the completed Global Project Initiation Document (PID) |  |  |  |  | COVBCD/ AFT
8 | Schedule weekly conference calls with Afton |  |  |  |  | COV/AFT
9 | Schedule weekly conference calls with BCD representatives |  |  |  |  | COVBCD
10 | Establish internal implementation team |  |  |  |  | COV
11 | Authorization for negotiated airline contracts - DRA/ATPCO process |  |  |  |  | AFT
12 | Advise client to alert all vendors with contracts of agency change |  |  |  |  | COV/AFT
13 | Determine deployment strategy of regional service - finalize check list |  |  |  |  | COVBCD/ AFT
14 | Apply for ARC license/certifications |  |  |  |  | COVBCD
15 | Review and revise global Afton policy requirements |  |  |  |  | COVBCD/ AFT
16 | Review and revise regional policy parameters |  |  |  |  | COVBCD/ AFT
17 | Discuss profile loading process (HR feed, manual entry, etc.) |  |  |  |  | COVBCD/ AFT
18 | Hold internal and client kick-off meetings - set ground rules, conference call etiquette, reiterate email communication, etc. |  |  |  |  | COV
19 | Discuss escalation process - responsibility |  |  |  |  | COV
20 | Discuss implementation expenses (budget, pricing considerations, responsibility for approvals) |  |  |  |  | COV
21 | Obtain customer holiday schedule for global project team |  |  |  |  | COV/AFT
22 | Determine usage of POS transaction fee: if set at global level or permitted to be established locally |  |  |  |  | COVBCD/ AFT
23 | Will fees be per transaction, per pnr, life of PNR, charging for splits, car/hotel only |  |  |  |  | COVBCD
24 | Afton Travel Policy distributed to International Rate Desk, Operations, |  |  |  |  | COVBCD
25 | Unique pseudo ordered and received from GDS as needed |  |  |  |  | COVBCD
26 | Request department list - hierarchy |  |  |  |  | COVBCD/ AFT
27 | Set up customer ID - account established |  |  |  |  | COVBCD
28 | Review reporting/accounting requirements - static and manual entry |  |  |  |  | COVBCD/ AFT
29 | Afton request for savings/reasons codes for review |  |  |  |  | COVBCD/ AFT
30 | Verify preferred vendors air, hotel and car rental discounts |  |  |  |  | COVBCD/ AFT
31 | Confirm KPI's, SLA's as required |  |  |  |  | COVBCD/ AFT
32 | Establish Afton Travel Portal - present for Afton review |  |  |  |  | COV
33 | Preferred vendor contacts delivered to COVBCD |  |  |  |  | COVBCD/ AFT
34 | Discuss project milestones |  |  |  |  | COVBCD/ AFT
35 | Request toll-free phone line(s) for 24/7 general and VIP |  |  |  |  | COVBCD
36 | Delivered preferred hotel rate listing to for HIC table loading |  |  |  |  | COVBCD
37 | Afton Travel Policy updated and attached to file |  |  |  |  | COV/AFT
38 | Review auto ticketing QC checks with online team and agent team |  |  |  |  | COVBCD
39 | Profile entry review, COVBCD processes |  |  |  |  | COVBCD/ AFT
40 | BCD meeting with Afton, determine official start date |  |  |  |  | COVBCD/ AFT
41 | Advise client to alert credit card vendor of agency change |  |  |  |  | COVBCD
42 | Determine local region airline contracts - receive copies |  |  |  |  | COVBCD/ AFT
43 | Determine Small Biz programs: need corporate id numbers |  |  |  |  | COVBCD/ AFT
44 | Add ARC/pseudos to airline hard and small biz agreements |  |  |  |  | COVBCD/ AFT
45 | Request client name list/e-mail addresses -VIP |  |  |  |  | COVBCD/ AFT
46 | Submit the On-Line Booking Product order form |  |  |  |  | COVBCD
47 | Define training and launch strategy for orientation |  |  |  |  | COVBCD/ AFT
48 | Review rollout communication methodology |  |  |  |  | COV/AFT
Task # | Weeks 4-6
49 | Review travel policies, identify regional differences and update |  |  |  |  | COVBCD/ AFT
50 | Confirm GDS client Star for accuracy |  |  |  |  | COVBCD/ AFT
51 | Direct process for installation of mobile apps and mobile notifications |  |  |  |  | COVBCD
52 | Establish dedicated Afton email address as needed |  |  |  |  | COV/AFT
53 | Confirm accounting fields - static and non for use by online and traditional agents |  |  |  |  | COVBCD/ AFT
54 | Review past air, hotel and car rental volumes and determine plan to maximize savings |  |  |  |  | COVBCD/ AFT
55 | Update project plan with milestones |  |  |  |  | COVBCD
56 | Notify 24-hour Emergency Service Centers of new client |  |  |  |  | COVBCD
57 | Discuss payment process - credit card designation |  |  |  |  | COV/AFT
58 | Increased staff confirmed for Fairfax support - August 1 start |  |  |  |  | COVBCD
59 | Global Account Manager and Client Services to meet with Afton to discuss timeline/duties |  |  |  |  | COVBCD/ AFT
60 | Confirm Afton phone config combined with COVBCD |  |  |  |  | COVBCD/ AFT
61 | Define traveler profile setup approach - HR feed or transfer |  |  |  |  | COVBCD
62 | Discuss PNR finishing requirements |  |  |  |  | COVBCD
63 | Setup traveler profiles |  |  |  |  | COVBCD
64 | Load discount data |  |  |  |  | COVBCD
65 | Load agency fees to profile |  |  |  |  | COVBCD
66 | Complete branding |  |  |  |  | COV
67 | Develop online help content |  |  |  |  | COV
Task # | Weeks 7-8
68 | Confirm ATPCO loading with airlines for release of data from COVBCD |  |  |  |  | COV
69 | Confirm designated agent grouping |  |  |  |  | COVBCD
70 | Schedule implementation/orientation session with travelers and travel coordinators |  |  |  |  | COVBCD/ AFT
71 | Confirm required accounting fields |  |  |  |  | COV/AFT
72 | Program online tool with policies and preferred vendors where applicable |  |  |  |  | COVBCD
73 | Program quality control systems with Afton policies and preferred vendors and test accuracy |  |  |  |  | COVBCD
74 | Test profile synchronization to GDS/online tool |  |  |  |  | COVBCD
75 | Review any pre trip authorization processes and hierarchy |  |  |  |  | COV/AFT
76 | Clarify policy violation codes |  |  |  |  | COV/AFT
77 | Clarify fare refusal and fare savings rules |  |  |  |  | COV/AFT
78 | Review reporting requirements |  |  |  |  | COVBCD/ AFT
79 | Create travel procedures instructions to publish on travel portal |  |  |  |  | COV
80 | Review required reporting |  |  |  |  | COVBCD/ AFT
81 | Discuss and clarify fare refusal and fare savings with client/agents and test online consistency |  |  |  |  | COVBCD
82 | Review Quality Control checks |  |  |  |  | COVBCD
83 | Online functional overview (WebEx meeting) |  |  |  |  | COV
84 | Deliver Online logins to project team |  |  |  |  | COV
85 | Select WebDirect sites to search |  |  |  |  | COVBCD
86 | Exclude vendors |  |  |  |  | COVBCD
87 | Plan training program |  |  |  |  | COV/AFT
88 | Review training curriculum |  |  |  |  | COV/AFT
89 | Print training materials |  |  |  |  | COV/AFT
90 | Schedule administrator training |  |  |  |  | COVBCD/ AFT
91 | Schedule travel coordinator training |  |  |  |  | COVBCD/ AFT
92 | Schedule user training |  |  |  |  | COVBCD/ AFT
Task # | Weeks 9 and 10
93 | Conference call with Afton to review progress |  |  |  |  | COV/AFT
94 | Meet with client locally to review timeline |  |  |  |  | BCD/AFT
95 | Discuss accounting data and verify reporting requirements |  |  |  |  | COVBCD/ AFT
96 | Test preferred vendor and discount accuracy |  |  |  |  | COVBCD
97 | Establish queue process with risk management/traveler tracking provider |  |  |  |  | COVBCD
98 | Review instructions for online user information training |  |  |  |  | COV
99 | Determine online survey processes and frequency |  |  |  |  | COV
100 | Review Afton Travel portal and check links |  |  |  |  | COVBCD
101 | Complete first agent training seminar |  |  |  |  | COVBCD
102 | Revise training curriculum as needed and schedule follow up training |  |  |  |  | COVBCD
103 | Validate PNR is finished correctly and in proper queue(s) |  |  |  |  | COVBCD
104 | Verify travel policy and approval/notification |  |  |  |  | COVBCD/ AFT
105 | Complete sign-off - of online tool |  |  |  |  | COVBCD
106 | Send introduction letter to travelers |  |  |  |  | COV/AFT
107 | Inform agents and support staff "go live" date |  |  |  |  | COVBCD
108 | Review with fulfillment center and 24-hour emergency service centers |  |  |  |  | COVBCD
109 | Establish Afton customized reports or dashboards |  |  |  |  | COVBCD
110 | Establish Afton Travel Portal and test |  |  |  |  | COVBCD
111 | Complete second agent training seminar |  |  |  |  | COV
112 | Review new report formats |  |  |  |  | COV/AFT
113 | Approve report formats |  |  |  |  | AFT
114 | Test run new reports |  |  |  |  | COVBCD
115 | Review profile set up, client passwords, procedures defined |  |  |  |  | COVBCD
116 | Establish email notification for online users as to traveler profile set up |  |  |  |  | COVBCD
117 | Establish timeline and deadlines for profile loading |  |  |  |  | COVBCD
118 | Test profile format and verify accounting information is loading correctly in GDS |  |  |  |  | COVBCD
119 | Test run QC checks |  |  |  |  | COVBCD
120 | Set up webex and onsite training schedule for users |  |  |  |  | COVBCD
121 | Online help desk review of procedures and Afton policies |  |  |  |  | COV
Task # | Week 11 and 12
122 | Review client vendor relationships and pricing in GDS |  |  |  |  | COVBCD
123 | Review check list of client profile with afterhours COVBCD office |  |  |  |  | COVBCD
124 | Review check list of procedures with online fulfillment desk/technical help desk |  |  |  |  | COVBCD
125 | Schedule ongoing management contacts and weekly/monthly/quarterly account updates and reviews |  |  |  |  | COV/AFT
126 | Finalize global SLA/KPI parameters |  |  |  |  | COV/AFT
127 | Verity Travel Authorization routine working properly |  |  |  |  | COV/AFT
128 | Verify Afton client portal is complete |  |  |  |  | COV
129 | Perform online user training onsite and via web conferencing |  |  |  |  | COVBCD/ AFT
130 | Review administrator access and knowledge of duties |  |  |  |  | COV/AFT
131 | Final training of Afton policies and procedures with designated travel consultants |  |  |  |  | COVBCD
132 | Test all vendor pricing within online tool and through traditional methods |  |  |  |  | COVBCD
133 | Verify accounting information for data collection |  |  |  |  | COVBCD
134 | Check QC processes for policy and vendor compliance for pricing/Afton requirements |  |  |  |  | COVBCD
135 | Profile loading initiated by travelers and users |  |  |  |  | COV/AFT
136 | Test profile data for accuracy in data loading |  |  |  |  | COVBCD
Official Start up of Afton

## Hotels
Sample Hotel Program
Comments | GDS Chain Code | Master Chain Code | Hotel Name | Address | City | State | Country | Currency | Room Type 1 Standard | Room Type 2 Upgrade | S1 RT1 LRA Single | S1 RT1 LRA Double | S1 RT2 LRA Single | S1 RT2 LRA Double | S2 RT1 LRA Single | S2 RT1 LRA Double | S2 RT2 LRA Single | S2 RT2 LRA Double | S3 RT1 LRA Single | S3 RT1 LRA Double | S3 RT2 LRA Single | S3 RT2 LRA Double | S4 RT1 LRA Single | S4 RT1 LRA Double | S4 RT2 LRA Single | S4 RT2 LRA Double | Cancel Policy | VAT/GST Included | Parking Included | Breakfast Included | On-Site Fitness Included | HSIA Included | Wireless Included | Airport Transfer Included | Office Transfer Included | Rate Valid for Contractors and Consultants | Sales Contact | Title | Email | RFP Submitter | Title | Email
| CY | EM | Courtyard Toronto Brampton | 90 Biscayne Crescent | Toronto-Brampton | ON | Canada | CAD | Standard/Standard |  | 132 | 132 |  |  | 132 | 132 |  |  | 132 | 132 |  |  | 132 | 132 |  |  | 6PM | N | Y | N | Y | Y | Y | N | N | Y | Brian Dec | Director of Sales Marketing | bdec@courtyardmarriottbrampton.com | Brian Dec | Director of Sales Marketing | bdec@courtyardmarriottbrampton.com
| SI | SW | Le Centre Sheraton Hotel Montreal | 1201 Bvld Rene-Levesque West | Montreal | QC | Canada | CAD | Standard | Concierge | 169 | 169 | 219 | 219 | [12 empty] | 6PM | N | N | N | Y | Y | Y | N | N | Y | Julie Dion | Business Travel Sales Manager | julie.dion@sheraton.com | Julie Dion | Business Travel Sales Manager | julie.dion@sheraton.com
| MC | EM | Marriott Copenhagen | 5 Kalvebod Brygge | Copenhagen |  | Denmark | DKK | Deluxe |  | 1350 | 1350 | [14 empty] | 24 Hours | Y | N | N | Y | N | Y | N | N | Y | Gitte Nødskov | Director of Sales and Marketing | gitte.nodskov@marriotthotels.com | Gitte Nødskov | Director of Sales and Marketing | gitte.nodskov@marriotthotels.com
| SH | SH | Scandic Front | Sankt Annae Plads 21 | Copenhagen |  | Denmark | DKK | Standard | Superior | 1110 | 1310 | 1410 | 1610 | [12 empty] | 6PM | Y | N | Y | Y | Y | Y | N | N | Y | ART Nordic ART Nordic | ART Nordic | artnordic@scandichotels.com | Art Nordic | Art Nordic | artnordic@scandichotels.com
Preferred Hotel |  |  | Albus Hotel Amsterdam City Centre | Vijzelstraat 49 | Amsterdam |  | Netherlands
Preferred Hotel |  |  | Mercure Amsterdam Airport | Oude Haagseweg 20 | Amsterdam |  | Netherlands
Preferred Hotel |  |  | NH Amsterdam Centre | 7 Stadhouderskade | Amsterdam |  | Netherlands
| RD | RD | Radisson Blu Hotel Amsterdam Airport | Boeing Ave 2 | Schiphol-Rijk |  | Netherlands | EUR | Standard |  | 175 | 175 | [14 empty] | 4PM | Y | N | N | Y | N | Y | Y | N | Y | Martijn Langstraat | Director Of Sales | Martijn.Langstraat@Radissonblu.com | Martijn Langstraat | Director Of Sales | Martijn.Langstraat@Radissonblu.com
Preferred Hotel |  |  | Thon Hotel Vika Atrium | Munkedamsveien 45 | Oslo |  | Norway
| SG | SG | Makati Shangri La | Ayala Crn Makati Avenues | Makati |  | Philippines | PHP | SUPERIOR | DELUXE | 9300 | 10500 | 10300 | 11500 | [12 empty] | 24 Hours | N | Y | N | Y | Y | Y | N | N | Y | Marion Espano-H. Del Pilar | Sales Manager | marionangeli.espano@shangri-la.com | N/A | N/A | N/A
Preferred Hotel |  |  | Danderyd Gasteri | Svardvagen 31 | Danderyd |  | Sweden
Preferred Hotel |  |  | Mornington Hotel Stockholm City | Nybrogatan 53 | Stockholm |  | Sweden
| CP | 6C | Crowne Plaza London St James | Buckingham Gate | London |  | United Kingdom | GBP | One Queen Bed | One King Bed | 165 | 165 | 190 | 190 | [12 empty] | 4PM | N | N | N | Y | Y | Y | N | N | Y | Maria Virlan | Sales Manager | mvirlan@cplonsj.co.uk | Maria Virlan | Sales Manager | mvirlan@cplonsj.co.uk
| UI | UI | Fraser Place Queens Gate | 39b Queens Gate Gardens | London |  | United Kingdom | GBP | Studio | Apartment | 135 | 135 | 165 | 165 | [12 empty] | 48 Hours | Y | N | N | N | N | Y | N | N | Y | Sin-Han Thiede |  | sinhan.thiede@frasershospitality.com
| LX | LX | Goring Hotel | Beeston Pl | London |  | United Kingdom | GBP | Standard | Superior | 229 | 269 | 319 | 319 | [12 empty] | 24 Hours | N | N | N | Y | N | N | N | N | Y | Tracy Ramsey | Director of Sales | salesdirector@thegoring.com | Nicky De Jesus
Preferred Hotel |  |  | The Alexander Pope Hotel | Cross Deep | Twickenham |  | United Kingdom
| HH | EH | Hilton Anchorage | 500 West Third Ave | Anchorage | AK | United States | USD | king and two beds |  | 99 | 99 | 99 |  | 181 | 181 |  |  | 99 | 99 | [6 empty] | 48 hours | N | N | N | N | N | N | N | N | Y | Scott Doonan | Director of Sales | scott.doonan@hilton.com
| RC | EM | Residence Inn Anchorage Midtown | 1025 35th Ave | Anchorage | AK | United States | USD | Studio |  | 99 | 99 |  |  | 181 | 181 |  |  | 99 | 99 | [6 empty] | 4PM | N | Y | Y | Y | Y | Y | Y | N | Y | Robert Hanson | Director of Sales | rob.hanson@nmsusa.com | Robert Hanson | Director of Sales | rob.hanson@nmsusa.com
| SI | SW | Sheraton Anchorage Hotel | 401 East 6th Ave | Anchorage | AK | United States | USD | Standard | Concierge | 99 | 99 | 129 | 129 | 199 | 199 | 229 | 229 | 99 | 99 | 129 | 129 |  |  |  |  | 6PM | N | N | N | Y | N | Y | N | Y | Y | Michael Jesperson | Sales Mgr | Michaeljesperson@remingtonhotels.com | Tanguy Libbrecht | Director of Sales & Marketing | tanguylibbrecht@remingtonhotels.com
Project Hotel | RC | EM | Residence Inn Dothan | 186 Hospitality Ln | Dothan | AL | United States | USD | Studio |  | 119 | 119 | [14 empty] | 4PM |  | Y | Y | Y | Y | Y | N | N | Y | Ashley Newton | Director of Sales | ashleyn@lbaproperties.com | Ashley Newton |  | ashleyn@lbaproperties.com
| MC | EM | Marriott Huntsville | 5 Tranquility Base | Huntsville | AL | United States | USD | Deluxe Guest |  | 139 | 139 | [14 empty] | 6PM | N | Y | N | Y | N | N | Y | N | Y | Kelly Beaty | Revenue Manager | Kelly.Beaty@marriott.com | Kelly Beaty | Revenue Manager | Kelly.Beaty@marriott.com
| BR | EM | Renaissance Agoura Hills | 30100 Agoura Rd | Agoura Hills | CA | United States | USD | Deluxe |  | 159 | 159 | [14 empty] | 6PM | N | Y | N | Y | Y | Y | N | Y | Y | KATHERINE MCKAY | Business Travel Sales Manager | kmckay@renaissanceagourahills.com | KATHERINE MCKAY | Business Travel Sales Manager | kmckay@renaissanceagourahills.com
| DT | EH | Doubletree By Hilton Livermore | 720 Las Flores Rd | Livermore | CA | United States | USD | One King Bed | 1 King Bed w/ref & micro | 94 | 94 | 99 | 99 | [12 empty] | 4PM | N | Y | Y | Y | Y | Y | N | N | Y | Annette Wright | Director of Sales | annette.wright@hilton.com | Annette Wright | Director of Sales | annette.wright@hilton.com
| RC | EM | Residence Inn San Diego San Marcos | 1245 Los Vallecitos Blvd | San Marcos | CA | United States | USD | Studio |  | 119 | 129 |  |  | 119 | 129 |  |  | 119 | 129 | [6 empty] | 6PM | N | Y | Y | Y | Y | Y | N | N | Y | Vincent Stubbs | Director of Sales | Vince.Stubbs@marriott.com | Vincent Stubbs | Director of Sales | Vince.Stubbs@marriott.com
| MC | EM | Marriott Colorado Springs | 5580 Tech Center Dr | Colorado Springs | CO | United States | USD | Deluxe Guest |  | 84 | 84 | [14 empty] | 24 Hours | N | Y | N | Y | N | N | N | Y | Y | CONNIE MILLER | BTS Manager | cmiller@marriottcoloradosprings.com | CONNIE MILLER | BTS Manager | cmiller@marriottcoloradosprings.com
| CY | EM | Courtyard Cocoa Beach Cape Canaveral | 3435 North Atlantic Ave | Cocoa Beach | FL | United States | USD | King/Queen Queen |  | 99 | 99 | [14 empty] | 6PM |  | Y | Y | Y | Y | Y | N | N | Y | Maria Sheldon | DOSM | maria.sheldon@courtyardcb.com | Maria Sheldon | DOSM | maria.sheldon@courtyardcb.com
Project Hotel | DT | EH | Doubletree By Hilton Cocoa Beach Oceanfront | 2080 North Atlantic Ave | Cocoa Beach | FL | United States | USD | Standard Ocean View |  | 115 | 115 | [14 empty] | 48 Hours |  | Y | N | Y | Y | Y | N | N | Y | Missy Helms | Revenue Manager | mhelms@sinc.com | Missy Helms |  | mhelms@sinc.com
Project Hotel | GI | EH | Hilton Garden Inn Orlando International Drive North | 5877 American Way | Orlando | FL | United States | USD | King or 2 Double Beds |  | 82 | [15 empty] | 16:00 |  | Y | Y | Y | Y | Y | N |  | Y | Michelle Wood | Director of Sales | ORLIH-SALESADM@hilton.com | Michelle Wood | Director of Sales | ORLIH-SALESADM@hilton.com
| MC | EM | Marriott Chicago Oak Brook | 1401 West 22nd St | Oak Brook | IL | United States | USD | Standard |  | 119 | 119 |  |  | 119 | 119 |  |  | 119 | 119 | [6 empty] | 6PM | N | Y | N | Y | Y | Y | N | N | N | Kris Glowczynski | Administrative Assistant | kris.glowczynski@marriott.com | Kris Glowczynski | Administrative Assistant | kris.glowczynski@marriott.com
| HG | EH | Homewood Suites By Hilton Cincinnati Airport South-Florence | 1090 Vandercar Way | Florence | KY | United States | USD | standard studio suite | one bedroom suite | 99 | 99 | 99 | 99 | [12 empty] | 24 Hours | N | Y | Y | N | Y | Y | Y | N | N | Sales Person |  | stacey.thomas@hilton.com | Stacey Thomas |  | stacey.thomas@hilton.com
| CY | EM | Courtyard Boston Andover | 10 Campanelli Dr | Andover | MA | United States | USD | King/QueenQueen |  | 89 | 89 |  |  | 89 | 89 |  |  | 89 | 89 |  |  | 89 | 89 |  |  | 6PM | N | Y | N | Y | Y | N | N | N | Y | Carol Morris | Administrative Assistant | carol.morris@marriott.com | Carol Morris | Administrative Assistant | carol.morris@marriott.com
| MC | EM | Marriott Boston Burlington | One Burlington Mall Rd | Burlington | MA | United States | USD | Deluxe |  | 169 | 169 | [14 empty] | 6PM | N | Y | N | Y | Y | N | N | Y | N | Carol Morris | Administrative Assistant | carol.morris@marriott.com | Carol Morris | Administrative Assistant | carol.morris@marriott.com
| HH | EH | Hilton Boston/Woburn | 2 Forbes Rd | Woburn | MA | United States | USD | one king bed or 2 doubles | one king or 2 double exec | 105 | 105 | 125 | 125 | [12 empty] | 6PM | N | Y | N | Y | Y | Y | N | Y | Y | Ivana Popovac | Corporate Sales Manager | ivana.popovac@hilton.com
| CY | EM | Courtyard By Marriott | 8910 Standford Blvd | Columbia | MD | United States | USD | King/QueenQueen |  | 159 | 159 | [14 empty] | 6PM | N | Y | N | Y | Y | Y | N | N | Y | Andria Stafford | Area Admin | andria.stafford@marriott.com | Andria Stafford | Area Admin | andria.stafford@marriott.com
| HX | EH | Hampton Inn Elkton | 2 Warner Rd | Elkton | MD | United States | USD | one king or two queens |  | 114 | 114 | [14 empty] | 24 Hours | N | Y | Y | N | Y | Y | N | N | N | Melissa Bailey |  | ELKMD_Hampton@hilton.com
| CY | EM | Courtyard Grand Rapids Airport | 4741 28th St Southeast | Kentwood | MI | United States | USD | King/QueenQueen |  | 119 | 119 | [14 empty] | 6PM | N | Y | N | Y | N | Y | Y | N | Y | Krista VanTol | General Manager | krista.vantol@whitelodging.com | Krista VanTol | General Manager | krista.vantol@whitelodging.com
| MC | EM | Marriott Minneapolis West | 9960 Wayzata Blvd | Minneapolis | MN | United States | USD | Deluxe |  | 139 | 139 | [14 empty] | 6PM | N | Y | N | Y | N | N | N | N | Y | MICHAEL DAVIS | Director of Sales | MDAVIS@CSMCORP.NET | MICHAEL DAVIS | Director of Sales | MDAVIS@CSMCORP.NET
| HX | EH | Hampton Inn & Suites Chillicothe | 100 North Plaza Blvd | Chillicothe | OH | United States | USD | Double Bedded Room | King Room | 90 | 90 | 100 | 100 | [12 empty] | 6PM |  | Y | Y | Y | Y | Y | N | N | Y | Andrea Digges | Director of Sales | CHLOH_hampton_suites@hilton.com | Andrea Digges |  | CHLOH_hampton_suites@hilton.com
| DT | EH | Doubletree Suites By Hilton Columbus Downtown | 50 South Front St | Columbus | OH | United States | USD | Standard |  | 149 | 149 | [14 empty] | 24 Hours | N | N | N | N | Y | Y | N | N | Y | Gina Suever Predovich | Sales Manger | gina.suever@hilton.com | Robert Kapala | Director of Sales | robert.kapala@hilton.com
| RC | EM | Residence Inn By Marriott Stillwater | 800 South Murphy St | Stillwater | OK | United States | USD | Studio Suite |  | 77 | [15 empty] | 4PM | N | Y | Y | Y | Y | Y | N | N | N | Cari Schaefer | Director Of Sales | cschaefer@aghospitality.com | Cari Schaefer | Director Of Sales | cschaefer@aghospitality.com
| GI | EH | Hilton Garden Inn Portland/Lake Oswego | 14850 Kruse Oaks Dr | Lake Oswego | OR | United States | USD | Standard K or Q/Q |  | 129 | 129 | [14 empty] | 6PM | N | Y | N | Y | Y | Y | N | Y | Y | Tiffany Block | Director of Sales | tiffany.block@hilton.com | Tiffany Block | Director of Sales | tiffany.block@hilton.com
| RC | EM | Residence Inn Philadelphia-Valley Forge | 600 West Swedesford Rd | Berwyn | PA | United States | USD | Studio 1 King Bed |  | 169 | [15 empty] | ck w/hotel |  | Y | N | Y | N | N | N | N
| CY | EM | Courtyard Philadelphia Valley Forge/King Of Prussi | 1100 Drummers Ln | Wayne | PA | United States | USD | King/Queen Queen |  | 139 | [15 empty] | 6PM |  | Y | N | Y | N | Y | N | N | Y | Kevin Cruley | Inventory Manager | Kevin.Cruley@marriott.com | Kevin Cruley |  | Kevin.Cruley@marriott.com
| FN | EM | Fairfield Inn & Suites Aiken | 185 Colony Pkwy | Aiken | SC | United States | USD | DoubleDouble/King |  | 92 | 92 | [14 empty] | 6PM | N | Y | Y | Y | Y | N | N | N | Y | Marylin Kline | Director of Sales | marylin.kline@nmrhospitality.com | Marylin Kline | Director of Sales | marylin.kline@nmrhospitality.com
| GI | EH | Hilton Garden Inn Greenville | 108 Carolina Point Parkway | Greenville | SC | United States | USD | Evolution |  | 82 | 82 | [14 empty] | 24 Hours |  | Y | Y | Y | Y | Y | Y |  | Y | Elise Romano | Director of Sales | elise.romano2@hilton.com | Elise Romano |  | Elise.romano2@hilton.com
| CY | EM | Courtyard Alexandria | 2700 Eisenhower Ave | Alexandria | VA | United States | USD | Deluxe/Deluxe |  | 189 | 189 | [14 empty] | 6PM | N | Y | N | Y | Y | Y | N | N | N | Kristen Danner | Area Sales Administrative Assistant | kristen.danner@marriott.com | Kristen Danner | Area Sales Administrative Assistant | kristen.danner@marriott.com
| HX | EH | Hampton Inn & Suites Alexandria Old Town Area South | 5821 Richmond Hwy | Alexandria | VA | United States | USD | 2 full size beds | King Studio Suite | 179 | 184 | 199 | 204 | [12 empty] | 4PM | N | Y | Y | N | Y | Y | Y | Y | Y | Micki Heineken | Director of Sales | WASAX_Hampton_Suites@hilton.com
| TO | EM | Towneplace Suites Chantilly Dulles South | 14036 Thunderbolt Pl | Chantilly | VA | United States | USD | Studio |  | 119 | 119 | [14 empty] | 6PM | N | Y | N | Y | Y | N | N | N | N | Noelle Karas | Area Sales Administrative Assistant | noelle.karas@marriott.com | Noelle Karas | Area Sales Administrative Assistant | noelle.karas@marriott.com
| MC | EM | Marriott Washington Dulles Airport | 45020 Aviation Dr | Dulles | VA | United States | USD | Deluxe |  | 168 | 168 | [14 empty] | 6PM | N | Y | Y | Y | Y | N | Y | N | N | Noelle Karas | Area Sales Administrative Assistant | noelle.karas@marriott.com | Noelle Karas | Area Sales Administrative Assistant | noelle.karas@marriott.com
| YX | YX | Ave Dulles Station | 2323 Dulles Station Blvd | Herndon | VA | United States | USD | One bedroom | Two Bedroom | 139 | 139 | 159 | 159 | [12 empty] | 24Hours | N | Y | Y | Y | Y | Y | N | N | Y | Lynn Madison | Corporate Sales Manager | lmadison@aveliving.com | Lynn Madison | Corporate Sales Manager | lmadison@aveliving.com
| ES | HE | Embassy Suites Dulles Airport | 13341 Woodland Park Dr | Herndon | VA | United States | USD | King size bed+ sofa | 2 Queen + sofa | 159 | 159 | 159 | 159 | [12 empty] | 18:00 | N | Y | Y | Y | Y | Y | Y | Y | Y | Lela gegia | Director of Sales | WASDA_DS@hilton.com
| HY | HY | Hyatt Dulles At Dulles International Air | 2300 Dulles Crn Blvd | Herndon | VA | United States | USD | Standard | Business Plan | 169 | 169 | 194 | 194 | [12 empty] | 24 Hours | N | Y | Y | Y | Y | Y | Y | Y | Y | Nasima Alam | Business Travel Sales Manage | nasima.alam@hyatt.com | Laurie Baldridge | Director, Worldwide Accounts | laurie.baldridge@hyatt.com
| HY | HY | Hyatt Place Herndon/Dulles Airport-East | 13711 Sayward Blvd | Herndon | VA | United States | USD | RunOfHouse |  | 139 | 139 | [14 empty] | 6PM | N | Y | Y | Y | Y | Y | Y | Y | Y | Demetra Milladge | Assistant Director of Sales and Marketing | dmilladge@otodevelopment.com | Mekdim Yemane | Director of Sales & Marketing | myemane@otodevelopment.com
| SI | SW | Sheraton Herndon Dulles Airport Hotel | 13715 Sayward Blvd | Herndon | VA | United States | USD | Standard |  | 139 | 139 | [14 empty] | 6PM | N | Y | N | Y | Y | Y | Y | Y | Y | Mekdim Yemane | Director of Sales and Marketing | myemane@otodevelopment.com
| WI | SW | The Westin Washington Dulles Airport | 2520 Wasser Terrace | Herndon | VA | United States | USD | Standard |  | 129 | 129 | [14 empty] | 4PM | N | Y | N | Y | Y | Y | Y | N | Y | Tami Crane | Director of Sales & Marketing | tami.crane@westinwashingtondulles.com
| CY | EM | Courtyard Tysons Corner Fairfax | 1960-A Chain Bridge Rd | Mclean | VA | United States | USD | King/DoubleDouble |  | 239 | 239 | [14 empty] | 4PM | N | Y | N | Y | Y | Y | N | N | Y | Cindy Fenn | Regional Director of Revenue Management | cindy.fenn@bfsaulco.com | Cindy Fenn | Regional Director of Revenue Management | cindy.fenn@bfsaulco.com
| HY | HY | Hyatt Regency Reston | 1800 Presidents St | Reston | VA | United States | USD | Standard |  | 229 | 229 | [14 empty] | 24 Hours | N | Y | N | Y | N | N | Y | N | Y | Robert Guevara | Sales Manager, Individual Trvl | rguevara@hyatt.com | Robert Guevara | Sales Mgr, Individual Trv | rguevara@hyatt.com
| WI | SW | The Westin Reston Heights | 11750 Sunrise Valley Dr | Reston | VA | United States | USD | Standard |  | 169 | [15 empty] | ck w/hotel |  |  |  |  | N | N | Y | N
Project Hotel | CY | EM | Courtyard Richland Columbia Point | 480 Columbia Point Dr | Richland | WA | United States | USD | King or Queen Bed |  | 119 | [15 empty] | 24 Hours |  | Y | N | Y | Y | Y | N |  | Y | Afra Mayfield | Director of Sales | amayfield@richlandmarriott.com | AfraMayfield | Director of Sales | amayfield@richlandmarriott.com

## Cars
Car | Corp Account | Leisure Account | Notes
Avis
Enterprise
Hertz |  |  | Direct Bill - only with approval from
(Vendor) |  |  | *10% off rate
(Vendor) |  |  | Direct Bill: Afton Systems does not have a direct bill account with
Carey. Afton does have a passenger credit card account which means each
passenger is responsible for paying for his/her trips.
Pricing: (Vendor) has special base rate pricing in it;s system for Afton:
Baltimore to/from Dulles AP: $100
Baltimore to/from Reagan National AP: $100
Washington, DC to/from Dulles AP: $78.20
Dulles Corridor to/from Dulles AP: $78.20
Dulles Corridor to/from Reagan National AP: $78.20
Dulles AP to/from Dulles AP: $78.20
Leesburg to/from Dulles AP:$86.70
Leesburg to/from Reagan National AP: $86.70
Reagan National AP to/from Reagan National AP: $52.70
The rates noted above do not include the STC, gratuity, airport fee (if any), fuel surcharge or any incidental items i.e. parking, tolls, cell phone usage, etc.

## Airlines
Airline Negotiated Rates | Type | Account # | Ticketing Instructions
United | Contract
Delta | Contract
American | Soft Dollar
British Air | Soft Dollar
Continental | Soft Dollar
Other
SAS | Soft Dollar
SWABIZ | Soft Dollar
Star Alliance - UK POS only | Soft Dollar

## Reason Codes
Mode | CODE | DEFINITION
CAR
| CC | Preferred car vendor not booked – Carrying Cargo
| CS | Preferred car vendor not booked – preferred vendor sold out
| CV | Preferred car vendor not booked - requested specific vendor
| CP | Preferred car size not booked – multiple passengers
| CL | Preferred car size not booked – preferred larger size
HOTEL
| HA | Accepted preferred hotel at negotiated rate
| HC | Covington negotiated rate
| HM | Meeting or convention rate
| HR | Lower rate at another property
| HX | No preferred hotel in city
| HL | Declined preferred hotel due to location
| HP | Declined preferred hotel due to personal preference
| HS | Preferred hotel sold out
AIR
| CD | Covington discount
| FT | Free Ticket
| NP | Negotiated program
| NS | No savings
| PS | Passenger Savings
| UT | Unused ticket
| WF | Web Fare
| DA | Declined airline
| DX | Declined connection/routing
| DE | Declined equipment
| DD | Declined date (min/max stay requirement)
| DP | Declined penalty fare
| DU | Declined time of day
| NL | No lower fare
| RC | Requested class of service
| RU | Requested fare for upgrade
| TA | Tardy travel authorization

## MI Info
Field | Description | Captured Via | Notes
Udid 1 | U1-Manager name - last name of Manager | HR Feed | Last name only - set up to 20 characters
Udid 2 | Department names: Executive, Customer Care, Finance, HR, IT, Legal, Marketing, DE, IS, GovCon Sales, GovCon Serv | HR Feed | This is the complete list - will be set up as a drop down menu
Udid 3 | Employee I.D. | HR Feed | Field of seven alpha/numerics as of April 2010; HR feed has 4-5 digits at this time
Udid 4 | Purpose of trip: external client, internal client, training, meeting or convention | POS
Udid 5 | Type of travel: billable or nonbillable | POS | Spell out (no codes) - will be set up as a drop down menu
Udid 6 | Approvers last name for all travel | POS | Set up to 20 characters; may be different than Manager name
Udid 7 | Project number | POS | Set for to 20 characters - free form text and numbers and "."
Udid 8 | Name of Client - if it's internal travel, they will use "Afton" as the client name | POS | Set for to 40 characters - free form text and numbers

## Travel Policy
Description | Notes